## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Group 48 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Yiyue Zeng | Hangjia Yu | Shiwen Huang | Xinyi Chen
Project Start Date: | 2021-09-14 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling Increment: | 1 | time axis 2021-09-15 to 2021-11-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-09-15 to 2021-11-09
Iteration 01
Iteration planning and meeting | Goal | Tiyue Zeng | 25% | 2021-09-14 | 1
Complete stakeholder register | High Risk | Hangjia Yu | 100% | 2021-09-15 | 5
Design persona | Low Risk | Xinyi Chen | 50% | 2021-09-20 | 8
Review and test persona | Med Risk | Shiwen Huang | 75% | 2021-09-24 | 4
Complete progress report | On Track | Shiwen Huang | 100% | 2021-09-28 | 2
Milestone 01 | Milestone |  | 10% | 2021-10-01 | 1
Iteration 02
Iteration planning and meeting | Low Risk | Tiyue Zeng | 60% | 2021-10-12 | 6
Complete gantt chart and search resources need | On Track | Xinyi Chen | 20% | 2021-10-12 | 3
Learn github board | Med Risk | Hangjia Yu | 33% | 2021-10-13 | 7
Review and test githuba | High Risk | Shiwen Huang | 14% | 2021-10-13 | 1 | 2021-10-13: 2; 2021-10-14: 2; 2021-10-15: 2; 2021-10-16: 2; 2021-10-17: 2; 2021-10-18: 2; 2021-10-19: 2; 2021-10-20: 2; 2021-10-21: 2; 2021-10-22: 2
Complete progress report | Goal | All of us | 100% | 2021-10-13 | 10
Iteration 03
Task 1Iteration planning and meeting | On Track | Shiwen Huang | 23% | 2021-10-15 | 6
Complete risk register | Med Risk | Xinyi Chen | 40% | 2021-10-15 | 14
Website integration | High Risk | Tiyue Zeng | 15% | 2021-10-15 | 6 | 2021-10-15: 2; 2021-10-16: 2; 2021-10-17: 2
Review and test | Goal | Xinyi Chen | 50% | 2021-10-15 | 3
Complete progress report | Low Risk | Hangjia Yu | 10% | 2021-10-15 | 10
TITLE 4
Task 1 |  |  |  | 2021-10-18 | 15
Task 2 |  |  |  | 2021-11-01 | 5
Task 3 | Milestone |  |  | 2021-12-13 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one
Formulas:
Xinyi Chen = [Xinyi Chen, row above]+14

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-10-15 |  |  |  |  | October | [20 empty] | November | [27 empty] | December
Scrolling Increment: | 1 | time axis 2021-10-16 to 2021-12-10
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
TITLE 1
Task 1 | Goal | Name | 25% | 2021-10-15 | 3 | S: 2; S: 2
Task 2 | Milestone |  |  | 2021-10-20 | 1 | bar: W
Task 3 | Low Risk |  | 50% | 2021-10-12 | 10
Task 4 | Milestone |  |  | 2021-11-04 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2021-10-21 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-10-21 | 13
Task 2 | On Track |  | 50% | 2021-10-23 | 9
Task 3 | Low Risk |  | 33% | 2021-10-28 | 11
Task 4 | Milestone |  |  | 2021-10-30 | 1 | bar: S
Task 5 |  |  |  | 2021-10-31 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-10-30 | 4
Task 2 | Med Risk |  |  | 2021-11-02 | 14
Task 3 | On Track |  |  | 2021-11-17 | 6
Task 4 | Goal |  |  | 2021-11-21 | 3 | S: 2; M: 2; T: 2
Task 5 | Low Risk |  |  | 2021-10-21 | 19
TITLE 4
Task 1 |  |  |  | 2021-11-24 | 15
Task 2 |  |  |  | 2021-12-08 | 5
Task 3 | Milestone |  |  | 2022-01-19 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-10-15 |  |  |  |  | October | [13 empty] | November | [27 empty] | December
Scrolling Increment: | 5 | time axis 2021-10-20 to 2021-12-14
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-10-20 to 2021-12-14
TITLE 1
Task 1 | Goal | Name | 25% | 2021-10-15 | 3
Task 2 | Milestone |  |  | 2021-10-20 | 1 | bar: 2021-10-20
Task 3 | Low Risk |  | 50% | 2021-10-12 | 10
Task 4 | Milestone |  |  | 2021-11-04 | 1 | bar: 2021-11-04
Task 5 | Med Risk |  | 10% | 2021-10-21 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-10-21 | 13
Task 2 | On Track |  | 50% | 2021-10-23 | 9
Task 3 | Low Risk |  | 33% | 2021-10-28 | 11
Task 4 | Milestone |  |  | 2021-10-30 | 1 | bar: 2021-10-30
Task 5 |  |  |  | 2021-10-31 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-10-30 | 4
Task 2 | Med Risk |  |  | 2021-11-02 | 14
Task 3 | On Track |  |  | 2021-11-17 | 6
Task 4 | Goal |  |  | 2021-11-21 | 3 | 2021-11-21: 2; 2021-11-22: 2; 2021-11-23: 2
Task 5 | Low Risk |  |  | 2021-10-21 | 19
TITLE 4
Task 1 |  |  |  | 2021-11-24 | 15
Task 2 |  |  |  | 2021-12-08 | 5
Task 3 | Milestone |  |  | 2022-01-19 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one